## Sheet1
2023-03-19 | Planning and finishing everything that can be written up without building | Cost analysis and Idea generation | Start buying necessary materials
2023-03-26 |  | Formalise (write up) cost analysis | Finish writing current practises | Write up High Resolution (Reductio ad Absurdum)
2023-04-02 |  | Proof read and "finalise" the writeup so far.
2023-04-09 | Building and write up remaining things | Subsystem 1 (Getting air quality sensors working)
2023-04-16
2023-04-23
2023-04-30 |  | Subsytem 1 write up
2023-05-07 |  | Subsystem 2 (Getting mobile platform working)
2023-05-14
2023-05-21
2023-05-28 |  | Subsytem 2 write up
2023-06-04 |  | Final integration
2023-06-11
2023-06-18
2023-06-25
2023-07-02
2023-07-09 | Final checks and tweaks
2023-07-16
2023-07-23
2023-07-30